## Instructions
Sprint Backlog Sheet
The Product Backlog defines the feature sets or features scoped for the given release iteration. However while detailing the release plan, the scoped features would be further drilled down and assigned to multiple sprints within a release. Once the features are allocated to multiple sprints, the sprint backlog would detail the tasks (engineering as well as technical) that are required to execute the requirements. Additionally the effort expounded for each task Vs the residual effort required to complete the remaining work are tracked on a daily basis as part of the sprint backlog. This would help in monitoring the actual progress made by the team in realizing the sprint goal.
Fill the following fields in the Sprint backlog sheet for each task
Task Number | <Provide the serial number for each task>
Task Name | <Provide the name of each task>. E.g. Develop design for XX Module
Product Backlog - Feature IDs | <Provide the Feature ID(s)of each task from the Product Backlog worksheet>
Estimated Start Date (dd-mmm-yy) | <Provide the estimated start date for each task>
Estimated End Date dd-mmm-yy) | <Provide the estimated end date for each task>
Responsible Person(s) | <Assign the person responsible to perform the task>
Task Dependency | <Provide the task number if the task has a dependency on another task>
Task Status | <Update the status of each task during the course of the sprint execution based on the below parameters:- Listed below are different task status:- Assigned – The identified task is allocated to a resource for implementation Start - The given task is initiated for implementation Complete – A task is deemed to be completed when the assigned functionality is implemented successfully as part of the sprint iteration. Re-Assigned – A task could be reallocated to another resource due to the unavailability of the original planned resource. Hold - The task might be put on hold due to certain constraints/ stakeholder's request, etc
Comments | <Provide the remarks/ comments for a task if any>
Initial Baseline Estimate (person hours) | <Provide the estimated effort (in person days) for each task that is identified within the Sprint Iteration> The initial baseline estimate value is provided for each task while creating the Sprint Plan. However this initial baseline estimate value would be zero if task(s) are newly added based on stakeholder inputs as prioritized in the product backlog for the current sprint. For such scenario's the latest baselined estimate field would only be updated.
New Estimate (person hours) | <Provide the revised estimate for the tasks if any> or <Provide the new estimate if a task is newly included in the Sprint Backlog after baselining the initial Sprint Backlog> The effort estimate for an existing task would be revisited for the following scenarios: a)During the course of sprint execution, the actual effort spent for the completed tasks as on date would be ascertained. Now based on this the estimate, the effort estimate for the succeeding or existing tasks could be re-estimated & updated in the 'new estimate' field. b) Based on the discussions with varied stakeholders & the complexity envisaged while implementing the features, the effort for the tasks could be re-estimated & updated in the 'new estimate' field. Hence the effort for an existing task as elaborated above could be revisited & the revised estimate is updated in the 'New Estimate' field & not in the 'Initial Baseline Estimate' field.

## Sprint Backlog
Sprint Backlog
Task Number | Task Name | Product Backlog - Feature IDs | Estimated Start Date (dd-mmm-yy) | Estimated End Date (dd-mmm-yy) | Responsible Person(s) | Task Dependency | Task Status | Comments | Initial Baseline Estimate (person hours) | New Estimate (person hours) | Change | Latest Baseline Estimate (person hours) | Amount Remaining (person hours) | Start | Start Day 1 | Start Day 2 | Start Day 3 | Start Day 4 | Start Day 5 | Start Day 6 | Start Day 7 | Start Day 8 | Start Day 9 | Start Day 10 | Start Day 11 | Start Day 12 | Start Day 13 | Start Day 14 | Start Day 15 | Start Day 16 | Start Day 17 | Start Day 18 | Start Day 19 | Start Day 20 | Start Day 21 | Start Day 22
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Note on P2: This is the first day of the sprint. All of the other days are based on this.